## Timeline
Bonanza Flat Planning and Easement Timeline:
Project Start Date June 15, 2017: Property Acquired
Task/Objective | 2017-06-01 | 2017-07-01 | 2017-08-17 | 2017-09-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18
Landowner/PCMC/Planning & Coordination
Planning Process Advisor/Stakeholder Groups | bar: 2017-08-17; 2017-10-17; 2017-12-17
Property Evaluation (Mine Hazzards/Environmental Concerns) | bar: 2017-06-01 to 2017-10-17
Quarterly Council Update (Public Meeting) | bar: 2017-07-01; 2017-10-17; 2017-12-17; 2018-02-18
Communications Plan (Public Outreach/Education) | bar: 2017-06-01 to 2018-02-18
Implement Capital Improvements | bar: 2018-06-18 to 2018-10-18
Baseline Documentation and Resource Inventory
Compile existing data and information on the property, existing boundary surveys | bar: 2017-06-01 to 2017-10-17
Design Survey for Public Input/ disseminate to voters and non profit coalition members to gain statistics on use and existing property perceptions | bar: 2017-06-01 to 2017-07-01
SOLICIT Public input through open houses | bar: 2017-06-01 to 2017-12-17
Conservation Value Mapping (Utilize existing heritage database, GAP info, Perigrine Fund and other data point sources, State Parks etc.) | bar: 2017-06-01 to 2017-10-17
Document Current Conditions/ground proof conservation value maps. (employ specialists and volunteer efforts for bird surveys/vegetative analysis, etc.) | bar: 2017-06-01 to 2017-10-17
Current Condition Analysis Mapping | bar: 2017-06-01 to 2017-10-17
Conservation Values Analysis Threats and Opportunities (could include separate weed mapping | bar: 2017-09-17 to 2017-12-17
Draft Report | bar: 2017-11-17 to 2017-12-17
Final Report | bar: 2017-12-17 to 2018-01-18
Conservation Easment Drafting
Review of Existing encumbrances | bar: 2017-06-01 to 2017-07-01
Initial Conservation Values assessment | bar: 2017-10-17 to 2017-11-17
Establish Easement zones if appropriate, determine recitals needed to accommodate stakeholder recognition | bar: 2017-10-17 to 2017-12-17
Draft Initial Conservation Easement | bar: 2017-12-17 to 2018-01-18
Review Survey data Compile stakeholder input | bar: 2017-09-17 to 2017-10-17
Prepare and Present Draft Conservation Easement for review by technical resources | bar: 2017-10-17 to 2017-11-17
Finalize Preservation Easement Draft incorporating edits | bar: 2017-11-17 to 2017-12-17
Review final document and Incorporate any additional Edits | bar: 2018-01-18 to 2018-02-18
Prepare and Present Preservation Easement and Management Plan to Park City Council ensure final edits. Record documents | bar: 2018-02-18 to 2018-04-18
Ensure Standards and Practices regarding appropriate board review and approval of Conservation Easement as per national standards are documented prior to signing and recordation. | bar: 2018-02-18 to 2018-03-18
Provide Comprehensive Project File to City including requisite approvals and minutes, recorded easement, baseline, baseline certification, mineral remoteness, etc. | bar: 2018-04-18
Comprehensive Adaptive Management & Stewardship Plan
Review of intended permitted preservation easement uses with Utah Open Lands staff | bar: 2017-12-17 to 2018-01-18
Recreation Mapping and Trails Plans including sensitive conservation area mapping | bar: 2017-10-17 to 2017-12-17
Recreation and trail assessment to provide appropriate strategies for conservation of sensitive areas | bar: 2017-10-17 to 2017-12-17
Riparian, Vegetative, Wildlife Assessments including aspen forest and Flammulated Owl evaluation | bar: 2017-06-01 to 2017-10-17
Invasive Weed Mapping | bar: 2017-06-01 to 2017-10-17
Invasive Weed removal and management strategy | bar: 2017-06-01 to 2017-11-17
Meetings with Technical committee | bar: 2017-06-01 to 2017-11-17
Identify appropriate and anticipated outreach specific to management strategies or suggestions which are supplemental to typical annual monitoring | bar: 2017-06-01 to 2017-11-17
Identify appropriate and anticipated monitoring protocols specific to management strategies or suggestions which are supplemental to typical annual monitoring | bar: 2017-06-01 to 2017-11-17
Provide Draft Management plan and edit plan with input from PC Staff | bar: 2017-11-17 to 2017-12-17
Provide Final Copy of Management plan Story map | bar: 2018-01-18 to 2018-02-18